METHOD STATEMENT

LV MAIN SWITCHBOARD AND CRITICAL POWER DISTRIBUTION

Main Switchboard LV dan Agihan Kritikal

| Document Information | Details |
| --- | --- |
| Project | [INSERT PROJECT NAME] |
| Employer / Client | [INSERT NAME] |
| Main Contractor | [INSERT NAME] |
| Consultant | [INSERT CONSULTANT ENGINEER / ARCHITECT] |
| Document No. | MS-DTC-002 |
| Revision / Date | Rev. 0 / [DD MMM YYYY] |

IMPORTANT: This is an editable starting template. A competent project team must adapt and approve it against the contract, approved drawings, project specification, actual site conditions, approved materials, manufacturer instructions, applicable Malaysian legal requirements and the Consultant’s submission procedure before work starts.

# DOCUMENT CONTROL

| Rev. | Date | Description | Prepared by | Checked by | Approved by |
| --- | --- | --- | --- | --- | --- |
| 0 | [Date] | Initial submission | [Name / Sign] | [Name / Sign] | [Name / Sign] |

# SUBMISSION STATUS

| Consultant Review | Tick / Comment |
| --- | --- |
| Approved | ☐ |
| Approved with comments | ☐ |
| Revise and resubmit | ☐ |
| Rejected | ☐ |

# 1. PURPOSE

This method statement defines the proposed controls, sequence, resources and inspection requirements for lv main switchboard and critical power distribution so that the work is executed safely, consistently and in accordance with the approved project requirements.

# 2. SCOPE

The scope covers preparation, material receipt, execution, inspection, testing, protection, records and handover associated with lv main switchboard and critical power distribution. Interfaces with preceding and following trades are included where they affect the quality or safety of the work.

# 3. REFERENCES AND PRECEDENCE

Contract documents, project specifications and latest approved construction drawings.

Approved material submissions, samples, shop drawings and coordination drawings.

Manufacturer’s current installation, storage, testing and maintenance instructions.

Approved Inspection and Test Plan, risk assessment, permits and project HSE plan.

Applicable Malaysian laws, authority requirements, standards and codes identified in the project specification.

Where requirements conflict, stop work and obtain written clarification from the Consultant before proceeding.

# 4. RESPONSIBILITIES

| Role | Minimum responsibility |
| --- | --- |
| Project Manager | Provide resources, approve the work plan and ensure interfaces are resolved. |
| Construction / Site Manager | Coordinate sequence, access, permits and daily execution. |
| Site Engineer | Confirm drawings, setting-out, technical controls and records. |
| QA/QC Engineer | Administer inspections, tests, hold points, non-conformance and handover records. |
| Safety and Health Personnel | Verify risk controls, briefings, permits and emergency readiness. |
| Supervisor / Foreman | Brief workers, control workmanship and maintain housekeeping. |
| Surveyor / Specialist | Perform assigned checks, testing or specialist work using calibrated equipment. |

# 5. MATERIALS

LV switchboards

Protection devices

Power cables or busduct

Earthing conductors

Labels

All permanent materials shall match approved submissions, be traceable where required and be stored to prevent damage or contamination.

# 6. PLANT, TOOLS AND EQUIPMENT

Lifting aids

Torque wrench

Primary injection set

Insulation tester

Thermal camera

Inspection and measuring equipment with valid calibration or verification status, where applicable.

Suitable access, lighting, barricades, environmental controls and emergency equipment.

# 7. PRE-START REQUIREMENTS

Latest approved documents are available at the work front and superseded information has been withdrawn.

Work area, access, preceding trade, datum and service interfaces have been inspected and released.

Materials are approved, undamaged, correctly stored and supported by required certificates.

The workforce is competent, briefed and equipped with task-specific personal protective equipment.

Risk assessment, permits, lifting arrangements and temporary works approvals are valid where applicable.

Inspection requests have been planned around hold and witness points; no work will be covered without release.

# 8. METHOD OF EXECUTION

## 8.1 Document and Work-Front Release

The Site Engineer shall confirm that the latest approved drawings, specifications, material submissions, coordination information and permits applicable to lv main switchboard and critical power distribution are available at the work front. The physical work area shall be jointly inspected with the Supervisor, QA/QC representative and affected trades. Any discrepancy in dimensions, levels, access, interfaces or site conditions shall be recorded and resolved in writing before physical work starts.

## 8.2 Resources, Competency and Daily Briefing

The Supervisor shall verify the workforce, specialist operatives, plant, access equipment and calibrated measuring devices against the planned daily output. A task briefing shall explain the approved sequence, individual responsibilities, exclusion zones, emergency arrangements, inspection points and stop-work conditions. Attendance and competency evidence shall be retained with the daily records.

## 8.3 Material Receipt, Storage and Traceability

Materials required for this activity shall be checked against the approved submission, delivery order, product identification and visible condition before acceptance. The following materials are expected: LV switchboards, Protection devices, Power cables or busduct, Earthing conductors, Labels. Items shall be segregated by type or batch, stored clear of contamination and damage, and issued to the work front in quantities that can be installed and protected during the shift. Rejected or unidentified materials shall be quarantined.

## 8.4 Activity Sequence

Carry out the physical works in the following sequence. The approved drawings, specification, temporary works design, lifting arrangement and manufacturer’s instructions govern where their requirements are more specific.

1. Approve discrimination study. Approve discrimination study, arc-flash requirements, panel arrangement and shutdown plan.

2. Receive, position, align. Receive, position, align and mechanically couple switchboard sections.

3. Install busbars, cables, control wiring, earthing. Install busbars, cables, control wiring, earthing and fire-stopped entries.

4. Torque and mark all joints. Torque and mark all joints before insulation and continuity testing.

5. Complete breaker, interlock, protection, metering. Complete breaker, interlock, protection, metering and communication tests.

6. Energise by controlled stages. Energise by controlled stages and conduct loaded thermal and power-quality checks.

Notes applicable to the entire Activity Sequence

Quality control: apply the controls to the complete Activity Sequence. Verify panel receipt; alignment; cable and busbar connections; torque and insulation; protection and interlocks; energisation and thermal scan against the approved drawings, specification, material data, agreed tolerances and Inspection and Test Plan. Obtain the required hold or witness point release before covering work or proceeding beyond a restricted stage.

Safety and interface control: maintain the approved risk controls, permits, access and exclusion zones for arc flash; live electricity; heavy lifting; incorrect phase sequence; unexpected energisation. Coordinate the work front with preceding and following trades, protect completed and adjoining work, and stop the activity when site conditions differ from the approved arrangement.

Records: retain the approved drawings and submissions, delivery and material traceability records, daily reports, inspection requests, checklists, test and survey results, permits, photographs, non-conformance close-out and handover records applicable to the complete Activity Sequence.

## 8.5 Final Inspection, Rectification and Protection

After completing the defined work section, the Supervisor and QA/QC representative shall carry out a systematic inspection from the approved checklist. Defects, incomplete interfaces, damage, contamination or work outside tolerance shall be marked and rectified using an accepted procedure. Completed work shall be protected from traffic, weather, impact, subsequent trades and premature loading until formal acceptance.

## 8.6 Testing, Records and Handover

The Site Engineer shall compile inspection requests, test reports, survey information, delivery and traceability records, permits, photographs, non-conformance close-out and as-built data applicable to the activity. The completed area shall be jointly handed over to the next trade or the Consultant only after all hold points, test results, comments and outstanding items have been closed or formally agreed.

# 9. INSPECTION AND QUALITY CONTROL

| Stage / Check | Acceptance basis | Record | Point |
| --- | --- | --- | --- |
| Panel receipt | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | H |
| Alignment | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | W |
| Cable and busbar connections | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | W |
| Torque and insulation | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | W |
| Protection and interlocks | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | W |
| Energisation and thermal scan | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | H |

H = Hold point: do not proceed without release. W = Witness point: provide notice and proceed only under the approved Inspection and Test Plan.

# 10. SAFETY, HEALTH AND ENVIRONMENT

| Hazard / Aspect | Minimum control |
| --- | --- |
| Arc flash | Apply the task risk assessment, competent supervision, exclusion zones and required permit. |
| Live electricity | Use inspected plant, suitable access and physical separation from people or live operations. |
| Heavy lifting | Wear task-specific PPE and control exposure at source through guarding, ventilation or wet methods. |
| Incorrect phase sequence | Provide a recovery plan, emergency communication and first-aid or rescue equipment suited to the risk. |
| Unexpected energisation | Apply the task risk assessment, competent supervision, exclusion zones and required permit. |
| Waste and pollution | Segregate waste, prevent discharge to drains, control spills and retain disposal records. |
| Noise, dust and nuisance | Use maintained equipment, suppression and approved working hours; monitor when required. |

# 11. NON-CONFORMANCE AND CORRECTIVE ACTION

Stop and identify work that does not meet the approved requirements.

Protect the affected area and raise the project’s non-conformance record where required.

Do not repair, remove or conceal non-conforming work until an authorised disposition is issued.

Reinspect and close the record with supporting evidence after corrective work.

# 12. RECORDS

Approved method statement, risk assessment, permits and toolbox briefing attendance.

Material approvals, delivery records, certificates and traceability records.

Inspection requests, checklists, survey records, test reports and calibration evidence.

Photographs, daily reports, non-conformance records, as-built information and handover documents.

# APPENDIX A — PRE-WORK CHECKLIST

| No. | Verification | Yes | No | N/A | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Approved drawings and specification available | ☐ | ☐ | ☐ |  |
| 2 | Material submission and sample approved | ☐ | ☐ | ☐ |  |
| 3 | Work area and preceding trade released | ☐ | ☐ | ☐ |  |
| 4 | Risk assessment and permits valid | ☐ | ☐ | ☐ |  |
| 5 | Resources, access and calibrated tools ready | ☐ | ☐ | ☐ |  |
| 6 | Hold / witness points and notice periods confirmed | ☐ | ☐ | ☐ |  |
| 7 | Interfaces with other trades coordinated | ☐ | ☐ | ☐ |  |
| 8 | Environmental and emergency controls ready | ☐ | ☐ | ☐ |  |

# APPENDIX B — PROJECT-SPECIFIC AMENDMENTS

Record every project-specific change made to this template before submission.

| Section | Project-specific requirement / change | Source / reference | Initial |
| --- | --- | --- | --- |