METHOD STATEMENT

HOLLOW CORE SLAB INSTALLATION

Pemasangan Hollow Core Slab

| Document Information | Details |
| --- | --- |
| Project | [INSERT PROJECT NAME] |
| Employer / Client | [INSERT NAME] |
| Main Contractor | [INSERT NAME] |
| Consultant | [INSERT CONSULTANT ENGINEER / ARCHITECT] |
| Document No. | MS-IBS-002 |
| Revision / Date | Rev. 0 / [DD MMM YYYY] |

IMPORTANT: This is an editable starting template. A competent project team must adapt and approve it against the contract, approved drawings, project specification, actual site conditions, approved materials, manufacturer instructions, applicable Malaysian legal requirements and the Consultant’s submission procedure before work starts.

# DOCUMENT CONTROL

| Rev. | Date | Description | Prepared by | Checked by | Approved by |
| --- | --- | --- | --- | --- | --- |
| 0 | [Date] | Initial submission | [Name / Sign] | [Name / Sign] | [Name / Sign] |

# SUBMISSION STATUS

| Consultant Review | Tick / Comment |
| --- | --- |
| Approved | ☐ |
| Approved with comments | ☐ |
| Revise and resubmit | ☐ |
| Rejected | ☐ |

# 1. PURPOSE

This method statement defines the proposed controls, sequence, resources and inspection requirements for hollow core slab installation so that the work is executed safely, consistently and in accordance with the approved project requirements.

# 2. SCOPE

The scope covers preparation, material receipt, execution, inspection, testing, protection, records and handover associated with hollow core slab installation. Interfaces with preceding and following trades are included where they affect the quality or safety of the work.

# 3. REFERENCES AND PRECEDENCE

Contract documents, project specifications and latest approved construction drawings.

Approved material submissions, samples, shop drawings and coordination drawings.

Manufacturer’s current installation, storage, testing and maintenance instructions.

Approved Inspection and Test Plan, risk assessment, permits and project HSE plan.

Applicable Malaysian laws, authority requirements, standards and codes identified in the project specification.

Where requirements conflict, stop work and obtain written clarification from the Consultant before proceeding.

# 4. RESPONSIBILITIES

| Role | Minimum responsibility |
| --- | --- |
| Project Manager | Provide resources, approve the work plan and ensure interfaces are resolved. |
| Construction / Site Manager | Coordinate sequence, access, permits and daily execution. |
| Site Engineer | Confirm drawings, setting-out, technical controls and records. |
| QA/QC Engineer | Administer inspections, tests, hold points, non-conformance and handover records. |
| Safety and Health Personnel | Verify risk controls, briefings, permits and emergency readiness. |
| Supervisor / Foreman | Brief workers, control workmanship and maintain housekeeping. |
| Surveyor / Specialist | Perform assigned checks, testing or specialist work using calibrated equipment. |

# 5. MATERIALS

Hollow core units

Bearing pads

Temporary props where designed

Grout and topping materials

All permanent materials shall match approved submissions, be traceable where required and be stored to prevent damage or contamination.

# 6. PLANT, TOOLS AND EQUIPMENT

Crane

Certified lifting clamps or beams

MEWP

Survey equipment

Inspection and measuring equipment with valid calibration or verification status, where applicable.

Suitable access, lighting, barricades, environmental controls and emergency equipment.

# 7. PRE-START REQUIREMENTS

Latest approved documents are available at the work front and superseded information has been withdrawn.

Work area, access, preceding trade, datum and service interfaces have been inspected and released.

Materials are approved, undamaged, correctly stored and supported by required certificates.

The workforce is competent, briefed and equipped with task-specific personal protective equipment.

Risk assessment, permits, lifting arrangements and temporary works approvals are valid where applicable.

Inspection requests have been planned around hold and witness points; no work will be covered without release.

# 8. METHOD OF EXECUTION

## 8.1 Document and Work-Front Release

The Site Engineer shall confirm that the latest approved structural drawings, hollow core erection drawings, unit schedule, lifting plan, temporary works design, material submissions and permits are available at the work front. The supporting structure, crane access, delivery route, bearing locations, levels, openings and interfaces shall be jointly inspected and released before erection starts.

## 8.2 Resources, Competency and Daily Briefing

Confirm the erection supervisor, crane operator, lifting supervisor, rigger, signaller, landing team, surveyor and grout or topping crew required for the planned bay. Verify competence, communication method, inspected lifting accessories, fall-protection arrangements, rescue provision and daily weather limits. Brief the team on the erection order, individual responsibilities, exclusion zones and stop-work conditions.

## 8.3 Material Receipt, Storage and Traceability

Check every hollow core unit, bearing pad, reinforcement item, grout and topping material against the approved submissions, delivery records and erection schedule. Maintain traceability to the unit mark and installation location. Store units on firm level supports at the positions stated by the manufacturer, with the stack height and dunnage alignment controlled to prevent twisting, cracking or strand damage.

## 8.4 Activity Sequence

Carry out the physical erection works in the following sequence. The approved erection drawing, lifting plan, temporary works design and manufacturer's instructions govern where their requirements are more specific.

Setting-out and bearing preparation. Transfer the approved grid lines, slab unit references and bearing lines to the supporting beams or walls. Check the support width, top level, surface condition and required bearing length against the approved erection drawings. Remove laitance, debris and local high spots, complete any approved make-good work, and install the specified bearing pads or levelling materials before a slab unit is lifted into position.

Delivery, unloading and unit identification. Receive the hollow core units in the planned erection order. Match each unit mark, length, depth, orientation and opening arrangement to the delivery schedule and erection drawing. Inspect the units for cracks, spalling, damaged ends, exposed strands, distorted lifting points or other transit damage. Place accepted units on firm, level dunnage positioned in line with the manufacturer's support points; segregate any rejected or doubtful unit.

Crane positioning and lifting arrangement. Position the crane on the approved standing area and confirm that the lifting radius, boom configuration and available capacity match the lifting plan. Establish the lifting and landing exclusion zones. Connect the certified lifting beam, clamps, slings or hooks only at the manufacturer's approved lifting locations. Use suitable tag lines to control rotation without placing personnel beneath the suspended unit.

Trial lift. Raise the unit slightly clear of the trailer or dunnage and hold it for a trial lift. Check that the load is balanced, all lifting accessories are correctly seated, the unit remains stable and there is no abnormal cracking or movement. Lower and adjust the rigging if the unit is not level or stable; do not continue the main lift until the lifting supervisor is satisfied.

Hoisting and slewing to the erection bay. Hoist the unit along the route defined in the lifting plan and maintain clear communication between the crane operator, lifting supervisor, rigger and landing team. Slew slowly near the structure and avoid shock loading, impact with columns or reinforcement, and dragging the unit across completed work. Stop the lift if wind, visibility, communication or access conditions become unsafe.

Landing on supports. Lower the unit under the direction of the designated signaller. Landing personnel shall guide the unit from a protected position using tag lines or approved tools and shall keep hands clear of pinch points. Seat both ends onto the correct bearing lines with the specified minimum bearing length and joint gap. Do not release the lifting accessories until the unit is fully supported and stable.

Alignment and level adjustment. Check the unit mark, orientation, end bearing, joint width, soffit alignment and top level immediately after landing. Make adjustments using approved methods while the crane remains connected where required. Do not hammer, lever against vulnerable edges, cut prestressing strands or pack the bearing with unapproved loose materials. Obtain technical direction for any unit that cannot be placed within the stated tolerances.

Temporary stability and progressive edge protection. Install the specified temporary restraint, bracing, ties or propping in the sequence shown on the erection or temporary works drawings. Provide edge protection and cover or barricade openings as each unit is placed; do not leave an unprotected leading edge for a later operation. Release the crane only after the temporary stability provisions for that unit are complete.

Continuation of erection. Erect the remaining units in the approved bay sequence, working from a stable completed area and maintaining the planned crane access. Check cumulative joint spacing and alignment frequently so dimensional drift is corrected before the closing unit is installed. Do not stockpile materials, operate access plant or impose construction loads on the units unless the temporary loading has been checked and authorised.

Keyways, reinforcement and end closures. Clean the longitudinal joints and bearing-end zones. Install the specified tie bars, continuity reinforcement, mesh, inserts, sleeves, fire-stopping components and end closures shown on the approved details. Coordinate openings and service penetrations before grouting. Site cutting, core drilling or chasing of a hollow core unit is prohibited unless a written specialist design and approval identifies the permitted location and method.

Joint grouting and structural topping. Pre-wet or otherwise prepare the joint surfaces as required by the approved grout system without leaving standing water. Place the approved grout continuously into keyways and end pockets, compact it to eliminate voids and finish it to the required level. Where a structural topping is specified, complete the reinforcement, level controls and pre-pour inspection before placing the concrete in a sequence that avoids local overloading. Cure and protect the grout or topping for the specified period.

Removal of temporary props and release of the floor. Remove temporary props, restraints or back-propping only after the specified grout or topping strength has been demonstrated and written release has been obtained from the responsible temporary works or design authority. Follow the approved depropping sequence to prevent sudden load transfer. Complete the final survey, close defects and formally release the floor before follow-on loading or trade access.

Notes applicable to the entire Activity Sequence

Quality control: the controls apply to the complete sequence. Verify unit identification and condition, support readiness, bearing length, joint width, soffit alignment, top level, temporary stability, reinforcement, grout or topping quality and the required strength before depropping. Record hold and witness point releases in accordance with the approved Inspection and Test Plan.

Safety and interface control: maintain the approved lifting plan, crane standing condition, weather limits, exclusion zones, fall protection, opening protection and temporary works throughout erection. Coordinate deliveries, crane movements, landing areas, structural supports, M&E openings, fire-stopping, façade interfaces and access for following trades. Stop work when conditions differ from the approved arrangement.

Records: retain the erection drawing and unit schedule, delivery and damage inspection records, lifting gear certificates, crane and lifting checklists, survey results, inspection requests, temporary works releases, grout or concrete test results, photographs, non-conformance close-out and final handover record.

## 8.5 Final Inspection, Rectification and Protection

After completing the erection bay, inspect unit condition, bearing, alignment, temporary stability, edge protection, joints, reinforcement, closures, grout or topping and curing. Mark and rectify defects using an approved repair procedure. Protect the completed floor from impact, contamination, weather and unapproved construction loading until formal release.

## 8.6 Testing, Records and Handover

Compile the delivery, erection, inspection, survey, temporary works, grout or concrete test, non-conformance and as-built records listed in the Activity Sequence notes. Hand over the completed bay only after the required strength, hold points, Consultant comments, edge protection and loading restrictions have been verified and communicated to the receiving trade.

# 9. INSPECTION AND QUALITY CONTROL

| Stage / Check | Acceptance basis | Record | Point |
| --- | --- | --- | --- |
| Support and bearing | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | H |
| Unit condition | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | W |
| Bearing length | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | W |
| Temporary stability | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | W |
| Keyway and grout | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | W |
| Topping and prop removal | Approved drawings, specification, material data and agreed tolerance | Inspection request / checklist / test report | H |

H = Hold point: do not proceed without release. W = Witness point: provide notice and proceed only under the approved Inspection and Test Plan.

# 10. SAFETY, HEALTH AND ENVIRONMENT

| Hazard / Aspect | Minimum control |
| --- | --- |
| Fall from height or open edge | Apply the task risk assessment, competent supervision, exclusion zones and required permit. |
| Suspended load | Use inspected plant, suitable access and physical separation from people or live operations. |
| Unit cracking | Wear task-specific PPE and control exposure at source through guarding, ventilation or wet methods. |
| Pinch points | Provide a recovery plan, emergency communication and first-aid or rescue equipment suited to the risk. |
| Temporary instability | Apply the task risk assessment, competent supervision, exclusion zones and required permit. |
| Waste and pollution | Segregate waste, prevent discharge to drains, control spills and retain disposal records. |
| Noise, dust and nuisance | Use maintained equipment, suppression and approved working hours; monitor when required. |

# 11. NON-CONFORMANCE AND CORRECTIVE ACTION

Stop and identify work that does not meet the approved requirements.

Protect the affected area and raise the project’s non-conformance record where required.

Do not repair, remove or conceal non-conforming work until an authorised disposition is issued.

Reinspect and close the record with supporting evidence after corrective work.

# 12. RECORDS

Approved method statement, risk assessment, permits and toolbox briefing attendance.

Material approvals, delivery records, certificates and traceability records.

Inspection requests, checklists, survey records, test reports and calibration evidence.

Photographs, daily reports, non-conformance records, as-built information and handover documents.

# APPENDIX A — PRE-WORK CHECKLIST

| No. | Verification | Yes | No | N/A | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Approved drawings and specification available | ☐ | ☐ | ☐ |  |
| 2 | Material submission and sample approved | ☐ | ☐ | ☐ |  |
| 3 | Work area and preceding trade released | ☐ | ☐ | ☐ |  |
| 4 | Risk assessment and permits valid | ☐ | ☐ | ☐ |  |
| 5 | Resources, access and calibrated tools ready | ☐ | ☐ | ☐ |  |
| 6 | Hold / witness points and notice periods confirmed | ☐ | ☐ | ☐ |  |
| 7 | Interfaces with other trades coordinated | ☐ | ☐ | ☐ |  |
| 8 | Environmental and emergency controls ready | ☐ | ☐ | ☐ |  |

# APPENDIX B — PROJECT-SPECIFIC AMENDMENTS

Record every project-specific change made to this template before submission.

| Section | Project-specific requirement / change | Source / reference | Initial |
| --- | --- | --- | --- |