WORK PACKAGE SUPPORTING DOCUMENTS

MS-TPL-007 — Trenchless-Pipeline Annulus Grouting

| Project | [Insert project name] | Document No. | MS-TPL-007-WP |
| --- | --- | --- | --- |
| Contractor | [Insert contractor] | Revision | 0 |
| Location | [Insert location] | Date | [DD/MM/YYYY] |
| Prepared by | [Name / Position] | Approved by | [Name / Position] |

This editable workbook must be adapted to the contract, approved drawings, project specification, actual site conditions, materials, equipment and authority requirements.

# 1. Inspection and Test Plan (ITP)

| Activity | Inspection / Test | Acceptance Criteria | Responsibility | H/W | Record |
| --- | --- | --- | --- | --- | --- |
| Approve grout type, annulus volume, bulkheads, stages, pressure limits, vents and contingency plan. | Grouting plan | Approved drawings, specification and submission | Site Engineer / QA/QC | H | IR / Checklist / Test Record |
| Survey the pipeline, seal entries and joints and install injection and vent points at verified elevations. | Seals and vents | Approved drawings, specification and submission | Site Engineer / QA/QC | W | IR / Checklist / Test Record |
| Batch grout to the approved density, flow and bleed criteria and confirm calibrated pressure monitoring. | Grout tests | Approved drawings, specification and submission | Site Engineer / QA/QC | W | IR / Checklist / Test Record |
| Inject from low points in controlled stages while observing vents, pipe movement, pressure and theoretical take. | Injection pressure | Approved drawings, specification and submission | Site Engineer / QA/QC | W | IR / Checklist / Test Record |
| Close vents only after consistent grout discharge and stop before pipe or ground pressure limits are exceeded. | Vent closure | Approved drawings, specification and submission | Site Engineer / QA/QC | W | IR / Checklist / Test Record |
| Top up after settlement where required and compile batch, volume, pressure, vent and completion records. | Volume and records | Approved drawings, specification and submission | Site Engineer / QA/QC | H | IR / Checklist / Test Record |

# 2. HIRARC

| Activity | Hazard | Consequence | Control | PIC |
| --- | --- | --- | --- | --- |
| Approve grout type, annulus volume, bulkheads, stages, pressure limits, vents and contingency plan. | Grout pressure | Injury / damage / delay | Permit, briefing, segregation, supervision and task-specific PPE | Supervisor / SHO |
| Survey the pipeline, seal entries and joints and install injection and vent points at verified elevations. | Pipe flotation | Injury / damage / delay | Permit, briefing, segregation, supervision and task-specific PPE | Supervisor / SHO |
| Batch grout to the approved density, flow and bleed criteria and confirm calibrated pressure monitoring. | Bulkhead failure | Injury / damage / delay | Permit, briefing, segregation, supervision and task-specific PPE | Supervisor / SHO |
| Inject from low points in controlled stages while observing vents, pipe movement, pressure and theoretical take. | Cement contact | Injury / damage / delay | Permit, briefing, segregation, supervision and task-specific PPE | Supervisor / SHO |
| Close vents only after consistent grout discharge and stop before pipe or ground pressure limits are exceeded. | Uncontrolled discharge | Injury / damage / delay | Permit, briefing, segregation, supervision and task-specific PPE | Supervisor / SHO |

# 3. Job Safety Analysis (JSA)

| Activity | Hazard | Consequence | Control | PIC |
| --- | --- | --- | --- | --- |
| Approve grout type, annulus volume, bulkheads, stages, pressure limits, vents and contingency plan. | Grout pressure | Injury / damage / delay | Permit, briefing, segregation, supervision and task-specific PPE | Supervisor / SHO |
| Survey the pipeline, seal entries and joints and install injection and vent points at verified elevations. | Pipe flotation | Injury / damage / delay | Permit, briefing, segregation, supervision and task-specific PPE | Supervisor / SHO |
| Batch grout to the approved density, flow and bleed criteria and confirm calibrated pressure monitoring. | Bulkhead failure | Injury / damage / delay | Permit, briefing, segregation, supervision and task-specific PPE | Supervisor / SHO |
| Inject from low points in controlled stages while observing vents, pipe movement, pressure and theoretical take. | Cement contact | Injury / damage / delay | Permit, briefing, segregation, supervision and task-specific PPE | Supervisor / SHO |
| Close vents only after consistent grout discharge and stop before pipe or ground pressure limits are exceeded. | Uncontrolled discharge | Injury / damage / delay | Permit, briefing, segregation, supervision and task-specific PPE | Supervisor / SHO |

# 4. Inspection Checklist

| No. | Inspection Item | What Must Be Checked | Status | Remarks / Evidence |
| --- | --- | --- | --- | --- |
| 1 | Grouting plan | Inspect grouting plan at every completed location. Confirm the approved type and detail, surface preparation, dimensions, spacing, embedment or engagement, tightening or curing, finish and required test record before the connection is concealed or loaded. | ☐ Conforming ☐ Non-conforming ☐ Not applicable |  |
| 2 | Seals and vents | Inspect seals and vents at every completed location. Confirm the approved type and detail, surface preparation, dimensions, spacing, embedment or engagement, tightening or curing, finish and required test record before the connection is concealed or loaded. | ☐ Conforming ☐ Non-conforming ☐ Not applicable |  |
| 3 | Grout tests | Confirm the test for grout tests uses the approved procedure, calibrated equipment, specified sampling location and required frequency. Record the measured result, acceptance limit, certificate number, witness or hold-point release and disposition of any failure. | ☐ Conforming ☐ Non-conforming ☐ Not applicable |  |
| 4 | Injection pressure | Confirm the test for injection pressure uses the approved procedure, calibrated equipment, specified sampling location and required frequency. Record the measured result, acceptance limit, certificate number, witness or hold-point release and disposition of any failure. | ☐ Conforming ☐ Non-conforming ☐ Not applicable |  |
| 5 | Vent closure | Inspect vent closure for each defined work lot. Confirm the correct location, completeness, cleanliness, damage-free condition and compliance with the approved drawing, specification, manufacturer's requirement and agreed sample. Record the result and close defects before release. | ☐ Conforming ☐ Non-conforming ☐ Not applicable |  |
| 6 | Volume and records | Inspect volume and records for each defined work lot. Confirm the correct location, completeness, cleanliness, damage-free condition and compliance with the approved drawing, specification, manufacturer's requirement and agreed sample. Record the result and close defects before release. | ☐ Conforming ☐ Non-conforming ☐ Not applicable |  |
| 7 | Work area released | Inspect work area released for each defined work lot. Confirm the correct location, completeness, cleanliness, damage-free condition and compliance with the approved drawing, specification, manufacturer's requirement and agreed sample. Record the result and close defects before release. | ☐ Conforming ☐ Non-conforming ☐ Not applicable |  |
| 8 | Final protection and handover | Inspect final protection and handover for each defined work lot. Confirm the correct location, completeness, cleanliness, damage-free condition and compliance with the approved drawing, specification, manufacturer's requirement and agreed sample. Record the result and close defects before release. | ☐ Conforming ☐ Non-conforming ☐ Not applicable |  |

# 5. Material Checklist

| No. | Item | Approval Details | Condition Details | Certificate / Calibration Details | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Cementitious or cellular grout | Match the approved material submission, technical data, manufacturer, product type, grade, size, colour where relevant, batch and intended location with the delivery documents. | Inspect identification, packaging, quantity, expiry where applicable, damage, deformation, corrosion, moisture, contamination and storage. Quarantine non-conforming material. | Check the manufacturer's certificate of conformity or analysis, batch number and shelf life; retain the safety data sheet, delivery docket and specified test results. |  |
| 2 | Approved admixtures | Match the approved material submission, technical data, manufacturer, product type, grade, size, colour where relevant, batch and intended location with the delivery documents. | Inspect identification, packaging, quantity, expiry where applicable, damage, deformation, corrosion, moisture, contamination and storage. Quarantine non-conforming material. | Check the manufacturer's certificate of conformity, product data, batch or serial identification and any specified test report. State 'not applicable' only with the QA/QC representative's agreement. |  |
| 3 | Vent pipes | Match the approved material submission, technical data, manufacturer, product type, grade, size, colour where relevant, batch and intended location with the delivery documents. | Inspect identification, packaging, quantity, expiry where applicable, damage, deformation, corrosion, moisture, contamination and storage. Quarantine non-conforming material. | Check the mill or manufacturer's certificate, grade and batch or heat number, product certification and required independent test report; verify traceability to the installed location. |  |
| 4 | Temporary bulkheads | Match the approved material submission, technical data, manufacturer, product type, grade, size, colour where relevant, batch and intended location with the delivery documents. | Inspect identification, packaging, quantity, expiry where applicable, damage, deformation, corrosion, moisture, contamination and storage. Quarantine non-conforming material. | Check the manufacturer's certificate of conformity, product data, batch or serial identification and any specified test report. State 'not applicable' only with the QA/QC representative's agreement. |  |
| 5 | Washout water | Match the approved material submission, technical data, manufacturer, product type, grade, size, colour where relevant, batch and intended location with the delivery documents. | Inspect identification, packaging, quantity, expiry where applicable, damage, deformation, corrosion, moisture, contamination and storage. Quarantine non-conforming material. | Check the manufacturer's certificate of conformity, product data, batch or serial identification and any specified test report. State 'not applicable' only with the QA/QC representative's agreement. |  |

# 6. Plant & Machinery Checklist

| No. | Item | Approval Details | Condition Details | Certificate / Calibration Details | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Colloidal mixer | Confirm the make, model, capacity, working range and attachment suit the approved method, lifting plan or temporary works design. Verify the assigned operator is trained and authorised. | Complete the pre-start check: structure, guards, controls, emergency stop, brakes, tyres or tracks, hoses, cables, leakage, warning devices and housekeeping. Tag out defects before use. | Verify plant registration where required, current inspection and maintenance record, operator competency and any electrical safety tag or manufacturer's verification applicable to the item. |  |
| 2 | Grout pump | Confirm the make, model, capacity, working range and attachment suit the approved method, lifting plan or temporary works design. Verify the assigned operator is trained and authorised. | Complete the pre-start check: structure, guards, controls, emergency stop, brakes, tyres or tracks, hoses, cables, leakage, warning devices and housekeeping. Tag out defects before use. | Verify the calibration or verification certificate matches the serial number, measurement range and accuracy required. Record calibration date, due date and pre-use functional check. |  |
| 3 | Pressure and flow gauges | Confirm the make, model, capacity, working range and attachment suit the approved method, lifting plan or temporary works design. Verify the assigned operator is trained and authorised. | Complete the pre-start check: structure, guards, controls, emergency stop, brakes, tyres or tracks, hoses, cables, leakage, warning devices and housekeeping. Tag out defects before use. | Verify the calibration or verification certificate matches the serial number, measurement range and accuracy required. Record calibration date, due date and pre-use functional check. |  |
| 4 | Density and bleed-test equipment | Confirm the make, model, capacity, working range and attachment suit the approved method, lifting plan or temporary works design. Verify the assigned operator is trained and authorised. | Complete the pre-start check: structure, guards, controls, emergency stop, brakes, tyres or tracks, hoses, cables, leakage, warning devices and housekeeping. Tag out defects before use. | Verify the calibration or verification certificate matches the serial number, measurement range and accuracy required. Record calibration date, due date and pre-use functional check. |  |
| 5 | Communication radios | Confirm the make, model, capacity, working range and attachment suit the approved method, lifting plan or temporary works design. Verify the assigned operator is trained and authorised. | Complete the pre-start check: structure, guards, controls, emergency stop, brakes, tyres or tracks, hoses, cables, leakage, warning devices and housekeeping. Tag out defects before use. | Verify plant registration where required, current inspection and maintenance record, operator competency and any electrical safety tag or manufacturer's verification applicable to the item. |  |

# 7. Manpower Requirement

Project Manager

Site Engineer

QA/QC Engineer

Safety and Health Officer

Supervisor

Skilled workers / operators

General workers

# 8. Required PPE

Safety helmet

Safety footwear

High-visibility vest

Safety gloves

Eye protection

Hearing / respiratory / fall protection where required

# 9. Required Permits

Permit to work

Work-front release

Lifting permit where applicable

Excavation / hot-work / confined-space permit where applicable

Inspection release before covering

# 10. Applicable Standards

Contract documents and project specification

Approved drawings and coordinated shop drawings

Approved material submissions and manufacturer instructions

Applicable Malaysian law and authority requirements

Applicable JKR specification where contractually required

Current project-approved MS/BS/EN/ISO standards

# 11. Inspection Records

| No. | Reference / Title | Revision | Date | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |

# 12. Testing Records

| No. | Reference / Title | Revision | Date | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |

# 13. Reference Drawings

| No. | Reference / Title | Revision | Date | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |

# 14. Document Register

| No. | Reference / Title | Revision | Date | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |